## Project Overview
Foodmandu Website Manual Testing Project
Field | Details
Project | Manual QA Testing of Foodmandu Web Application
Target Website | https://foodmandu.com/
Project Type | Portfolio-ready black-box manual testing project
Last Updated | 2026-08-21
Primary Goal | Validate critical customer journeys, usability, input validation, content consistency, and order-related flows without submitting unauthorized real orders.
Test Approach | Functional, UI, validation, negative, boundary, exploratory, compatibility, accessibility smoke, and basic security-oriented black-box checks.
Execution Status | Execution reviewed: 89 Pass, 2 Fail, 1 N/A, 0 Not Executed. Two Medium-severity defects are open. Pass rate across applicable executed tests: 97.8%.
Scope
In Scope | Home page; restaurant/cuisine search; restaurant listing; filters/sorting; restaurant detail/menu; food-item search; authentication; registration; forgot password; cart; delivery details; order review; delivery charges; help/footer content; responsive behavior; accessibility smoke checks.
Out of Scope | Admin/back-office systems; restaurant partner portal; destructive testing; load testing; payment capture; placing real paid orders; social-login account creation without authorization.
Safety Constraint | Do not complete an order that creates a real charge or operational delivery unless you have explicit authorization and a disposable test account/address.
Verified Public Product Notes Used for Test Design
Source | Verified public information
https://foodmandu.com/ | Homepage exposes restaurant/cuisine search, featured restaurants, login, help links, and service hours.
https://foodmandu.com/Restaurant/Index | Restaurant listing exposes filters, cuisine filtering, sorting, and no-results states.
https://foodmandu.com/Account/Login | Login supports email/password, Remember Me, Facebook, Google, Sign Up, and Forgot Password.
https://foodmandu.com/Account/register | Registration asks for first name, last name, email, mobile, password, confirm password, and terms agreement.
https://foodmandu.com/Home/HowToOrder | Official flow describes choosing a restaurant, selecting food, entering delivery details/date/time, and confirming an order.
https://foodmandu.com/Home/DeliveryCharge | Published delivery charge: Rs. 20 up to 1 km, then additional Rs. 20/km; Foodmandu Fresh Rs. 100/order.

## Test Plan
Manual Test Plan
1. Objective
Verify that Foodmandu's customer-facing website supports reliable restaurant discovery, account access, menu browsing, cart/order preparation, delivery information, and supporting help content.
2. Entry Criteria
Website is reachable; test browser has internet access; no major outage; test data is available; tester understands that real order submission is excluded unless authorized.
3. Exit Criteria
All Critical/High-priority cases executed; no open Critical defects; major customer journeys covered; all defects recorded with reproducible steps and evidence.
4. Test Techniques
Equivalence partitioning, boundary value analysis, positive/negative testing, state transition checks, exploratory testing, error guessing, usability review, and responsive UI checks.
5. Browsers / Devices
Desktop: latest Chrome, Edge, Firefox. Mobile smoke: Chrome Android or responsive emulation at ~360x800 and ~390x844. Optional Safari/iOS if available.
6. Test Data
Use non-sensitive test names, disposable email where permitted, Nepali mobile-format examples, invalid/boundary inputs, and a safe delivery address only if proceeding to checkout without final submission.
7. Defect Severity
Critical: blocks ordering/login or causes data/security loss. High: major flow broken with no practical workaround. Medium: feature partially broken. Low: cosmetic/content/usability issue.
8. Defect Priority
P0 immediate; P1 high; P2 normal; P3 low.
9. Risks
Live restaurant availability changes; menu items/prices can change; geolocation/delivery values vary; client-side rendering may differ from indexed HTML; social login requires external accounts.
10. Deliverables
Test plan, scenarios, detailed test cases, RTM, test data, execution dashboard, exploratory charters, and defect log.

## Test Scenarios
Scenario ID | Module | Scenario | Priority | Test Type | Coverage Goal | Execution Result
TS-001 | Homepage | Verify homepage loads and core navigation is available | High | Functional/UI | Critical entry points | Pass
TS-002 | Search | Verify restaurant/cuisine search with valid keywords | Critical | Functional | Discovery | Pass
TS-003 | Search | Verify search with invalid, empty, whitespace, and special-character input | High | Negative/Boundary | Validation | Pass
TS-004 | Restaurant Listing | Verify restaurant results display relevant information | High | Functional/UI | Discovery | Pass
TS-005 | Restaurant Listing | Verify cuisine filters and filter reset behavior | High | Functional | Filtering | Pass
TS-006 | Restaurant Listing | Verify sorting behavior | Medium | Functional | Sorting | Pass
TS-007 | Restaurant Listing | Verify no-results state | Medium | Negative/UI | Error state | Pass
TS-008 | Restaurant Detail | Verify restaurant detail, delivery hours, fees, and menu information | Critical | Functional/UI | Restaurant selection | Fail
TS-009 | Menu | Verify menu category navigation and food-item search | High | Functional | Menu discovery | Pass
TS-010 | Cart | Verify adding a food item to cart | Critical | Functional | Cart creation | Pass
TS-011 | Cart | Verify quantity update and removal | Critical | Functional | Cart management | Pass
TS-012 | Cart | Verify price calculations and totals | Critical | Functional/Data | Commerce accuracy | Pass
TS-013 | Authentication | Verify login positive and negative paths | Critical | Functional/Negative | Access | Pass
TS-014 | Registration | Verify registration validation and account creation flow | High | Functional/Boundary | Account creation | Pass
TS-015 | Forgot Password | Verify forgot-password validation and feedback | High | Functional/Negative | Recovery | Pass
TS-016 | Checkout | Verify delivery detail fields and validations | Critical | Functional/Boundary | Order preparation | Pass
TS-017 | Checkout | Verify order review before final confirmation | Critical | Functional/Data | Order accuracy | Pass with N/A
TS-018 | Delivery | Verify published delivery-charge rules and presentation | High | Functional/Content | Fee transparency | Pass
TS-019 | Help & Content | Verify About, FAQs, How to Order, Terms, Privacy, Contact links | Medium | Content/Navigation | Trust/support | Fail
TS-020 | Responsive UI | Verify primary flows at desktop and mobile widths | High | Compatibility/UI | Responsive use | Pass
TS-021 | Accessibility | Run keyboard, focus, labels, contrast, and zoom smoke checks | Medium | Accessibility | Basic WCAG-oriented checks | Pass
TS-022 | Security Smoke | Verify password masking, error-message leakage, HTTPS, and basic input handling | High | Security/Negative | Black-box security smoke | Pass
TS-023 | Session | Verify Remember Me, logout/session behavior where available | High | Functional/Security | Session handling | Pass
TS-024 | External Auth | Verify Google/Facebook auth entry points open correctly without completing unauthorized signup | Medium | Integration | External auth | Pass
TS-025 | Exploratory | Explore customer journey from search to pre-confirmation checkout | Critical | Exploratory | End-to-end risk discovery | Charter Only

## Test Cases
TC ID | Module | Scenario ID | Test Case | Preconditions | Steps | Test Data | Expected Result | Priority | Type | Status | Actual Result | Defect ID | Notes
TC-001 | Homepage | TS-001 | Open Foodmandu homepage | Internet available | 1. Navigate to https://foodmandu.com/ 2. Observe page load | N/A | Homepage loads without fatal error; branding, search, featured restaurants, Login and footer/help links are available. | Critical | Smoke | Pass | Observed behavior matched the expected result.
TC-002 | Homepage | TS-001 | Verify restaurant/cuisine search input is visible | Homepage loaded | Locate main search control | N/A | Search field and Find Restaurants action are visible and usable. | High | UI | Pass | Observed behavior matched the expected result.
TC-003 | Homepage | TS-001 | Open a featured restaurant | Homepage loaded | Select one featured restaurant card | Any visible featured restaurant | Restaurant detail page opens for the selected restaurant. | High | Navigation | Pass | Observed behavior matched the expected result.
TC-004 | Homepage | TS-001 | Verify footer help links | Homepage loaded | Open About Us, Delivery Charges, How to Order, FAQs, Contact, Terms, Privacy one by one | N/A | Each link routes to the intended page without 404/error. | Medium | Navigation | Pass | Observed behavior matched the expected result.
TC-005 | Homepage | TS-001 | Verify service hours display | Homepage loaded | Scroll to footer and read service hours | N/A | Service hours are displayed consistently and legibly. | Low | Content | Pass | Observed behavior matched the expected result.
TC-006 | Search | TS-002 | Search by restaurant name | Homepage loaded | Enter known restaurant name; submit search | Fire And Ice | Relevant matching restaurant(s) appear. | Critical | Functional | Pass | Observed behavior matched the expected result.
TC-007 | Search | TS-002 | Search by cuisine | Homepage loaded | Enter cuisine keyword; submit | Pizza | Results include restaurants/products relevant to pizza. | High | Functional | Pass | Observed behavior matched the expected result.
TC-008 | Search | TS-002 | Search is case-insensitive | Homepage loaded | Search same keyword using different casing | pizza / PIZZA | Results are logically equivalent or search handles casing gracefully. | Medium | Functional | Pass | Observed behavior matched the expected result.
TC-009 | Search | TS-003 | Search with empty input | Homepage loaded | Leave search empty; submit | Blank | System prevents meaningless search or returns a sensible default/list without error. | Medium | Negative | Pass | Observed behavior matched the expected result.
TC-010 | Search | TS-003 | Search with spaces only | Homepage loaded | Enter spaces; submit | 238 | Whitespace is trimmed or handled without crash. | Medium | Negative | Pass | Observed behavior matched the expected result.
TC-011 | Search | TS-003 | Search with special characters | Homepage loaded | Enter special characters; submit | @#$%^ | No script/error leakage; safe no-results or sanitized behavior. | High | Security/Negative | Pass | Observed behavior matched the expected result.
TC-012 | Search | TS-003 | Search with long input | Homepage loaded | Paste a 250-character query; submit | 250-char string | UI remains stable; input is bounded/handled; no server error. | Medium | Boundary | Pass | Observed behavior matched the expected result.
TC-013 | Search | TS-003 | Search with common injection-like string | Homepage loaded | Enter harmless SQL-like text as plain input | OR 1=1 -- | Input is treated as text; no sensitive error or unexpected data exposure. | High | Security/Negative | Pass | Observed behavior matched the expected result.
TC-014 | Restaurant Listing | TS-004 | Verify restaurant result cards | Restaurant listing loaded | Inspect several result cards | N/A | Cards display useful restaurant identity/location/cuisine data without broken placeholders. | High | UI | Pass | Observed behavior matched the expected result.
TC-015 | Restaurant Listing | TS-005 | Filter by one cuisine | Restaurant listing loaded | Select one cuisine filter; apply | Pizza | Only matching/relevant restaurants remain or filter behavior is clearly reflected. | High | Functional | Pass | Observed behavior matched the expected result.
TC-016 | Restaurant Listing | TS-005 | Apply multiple filters if supported | Restaurant listing loaded | Select more than one available filter; apply | Two available cuisines/options | Results reflect combined filter logic without error. | Medium | Functional | Pass | Observed behavior matched the expected result.
TC-017 | Restaurant Listing | TS-005 | Clear/reset filters | Filter applied | Clear filters or restore default | N/A | Full/default result set returns. | High | Functional | Pass | Observed behavior matched the expected result.
TC-018 | Restaurant Listing | TS-006 | Change sort option | Restaurant listing loaded | Choose a different Sort By option | Any non-default option | List order changes according to selected sort rule. | Medium | Functional | Pass | Observed behavior matched the expected result.
TC-019 | Restaurant Listing | TS-007 | Verify no-results message | Restaurant listing loaded | Use unlikely search/filter combination | zzzz_nonexistent_987 | Clear no-results feedback is shown and page remains usable. | Medium | Negative/UI | Pass | Observed behavior matched the expected result.
TC-020 | Restaurant Listing | TS-004 | Open restaurant from result list | Results visible | Select a restaurant result | Any open restaurant | Correct restaurant detail page opens. | High | Navigation | Pass | Observed behavior matched the expected result.
TC-021 | Restaurant Detail | TS-008 | Verify restaurant delivery hours | Restaurant page loaded | Inspect delivery hours summary and weekly hours | N/A | Hours are displayed clearly and do not contradict within the same page. | High | Content | Pass | Observed behavior matched the expected result.
TC-022 | Restaurant Detail | TS-008 | Verify minimum order format | Restaurant page loaded | Inspect minimum-order field | N/A | A valid currency value or clear 'No minimum' message is shown; malformed values such as 'Rs. .00' are not shown. | Medium | Data/UI | Fail | Minimum order was displayed as 'Rs. .00', which is a malformed currency value. | BUG-001 | Confirmed during manual execution. See BUG-001 in Defect Log.
TC-023 | Restaurant Detail | TS-008 | Verify service charge and VAT labels | Restaurant page loaded | Inspect service charge and VAT values | N/A | Each displays a valid percentage/value or clear N/A consistently. | Medium | Data/UI | Pass | Observed behavior matched the expected result.
TC-024 | Menu | TS-009 | Search food items within restaurant | Restaurant page loaded | Use Search Food Items with known menu keyword | Pizza | Matching menu items are filtered/displayed. | High | Functional | Pass | Observed behavior matched the expected result.
TC-025 | Menu | TS-009 | Food-item search no-results state | Restaurant page loaded | Search a non-existent item | zzzz123 | Clear no-results feedback; no crash. | Medium | Negative | Pass | Observed behavior matched the expected result.
TC-026 | Menu | TS-009 | Navigate menu categories | Restaurant page with categories loaded | Select category/subcategory | Any available category | Menu moves/filters to chosen category correctly. | High | Functional | Pass | Observed behavior matched the expected result.
TC-027 | Restaurant Detail | TS-008 | Verify item price presentation | Restaurant page loaded | Inspect several food items | N/A | Prices use consistent NPR/Rs. formatting and no raw template placeholders are visible. | Critical | Data/UI | Pass | Observed behavior matched the expected result.
TC-028 | Restaurant Detail | TS-008 | Verify restaurant close state | Open a closed restaurant if available | Inspect ordering controls | Closed restaurant | Closed status is clear; ordering unavailable or appropriately constrained. | High | State Transition | Pass | Observed behavior matched the expected result.
TC-029 | Restaurant Detail | TS-008 | Verify branch links | Restaurant with branches if available | Open another branch | N/A | Correct branch restaurant page opens; branch identity is clear. | Low | Navigation | Pass | Observed behavior matched the expected result.
TC-030 | Cart | TS-010 | Add one available food item to cart | Open restaurant; item available | Click Add/plus action for one item | 1 menu item | Cart is created and selected item appears with correct name, price, quantity. | Critical | Functional | Pass | Observed behavior matched the expected result.
TC-031 | Cart | TS-010 | Add multiple different items | Cart has one item | Add two different items | 3 distinct items | All items appear without duplication/corruption. | Critical | Functional | Pass | Observed behavior matched the expected result.
TC-032 | Cart | TS-011 | Increase item quantity | Cart contains item | Increase quantity once | Qty 1 -> 2 | Quantity becomes 2 and line subtotal updates. | Critical | Functional | Pass | Observed behavior matched the expected result.
TC-033 | Cart | TS-011 | Decrease item quantity | Item quantity > 1 | Decrease quantity | Qty 2 -> 1 | Quantity decreases and totals update. | Critical | Functional | Pass | Observed behavior matched the expected result.
TC-034 | Cart | TS-011 | Remove item from cart | Cart contains item | Use remove/delete action | N/A | Item is removed and total recalculates. | Critical | Functional | Pass | Observed behavior matched the expected result.
TC-035 | Cart | TS-011 | Remove final item | Cart contains exactly one item | Remove final item | N/A | Cart becomes empty and appropriate empty-cart state is shown. | High | State Transition | Pass | Observed behavior matched the expected result.
TC-036 | Cart | TS-012 | Verify line subtotal calculation | Cart contains quantity >1 | Compare item price x quantity with subtotal | Price 250, Qty 2 | Displayed subtotal equals price × quantity. | Critical | Data | Pass | Observed behavior matched the expected result.
TC-037 | Cart | TS-012 | Verify order subtotal after multiple items | Cart has multiple items | Manually sum line subtotals and compare | N/A | Order subtotal equals sum of line subtotals. | Critical | Data | Pass | Observed behavior matched the expected result.
TC-038 | Cart | TS-012 | Verify cart persists during normal navigation | Cart contains items | Navigate to another page then return to cart | N/A | Cart remains intact within expected session behavior. | High | Session | Pass | Observed behavior matched the expected result.
TC-039 | Cart | TS-010 | Attempt adding item from another restaurant | Cart already contains first restaurant item | Open another restaurant and add item | Two different restaurants | System follows its business rule clearly, e.g. warns/replaces/separates cart without silent data loss. | High | Business Rule | Pass | Observed behavior matched the expected result.
TC-040 | Authentication | TS-013 | Login with valid credentials | Registered test account exists | Enter valid email/password; login | Authorized test account | User is authenticated and redirected appropriately. | Critical | Positive | Pass | Observed behavior matched the expected result.
TC-041 | Authentication | TS-013 | Login with invalid password | Known email | Enter correct email and wrong password | Wrong password | Login fails with clear non-sensitive error. | Critical | Negative | Pass | Observed behavior matched the expected result.
TC-042 | Authentication | TS-013 | Login with invalid email format | Login page loaded | Enter malformed email and any password | abc@ | Validation prevents/flags invalid email. | High | Validation | Pass | Observed behavior matched the expected result.
TC-043 | Authentication | TS-013 | Login with blank fields | Login page loaded | Submit both fields blank | Blank | Required-field feedback is shown. | High | Negative | Pass | Observed behavior matched the expected result.
TC-044 | Authentication | TS-013 | Password field masking | Login page loaded | Type password | Secret123! | Password characters are masked. | High | Security/UI | Pass | Observed behavior matched the expected result.
TC-045 | Authentication | TS-023 | Remember Me checkbox | Valid account | Select Remember Me and login; close/reopen browser according to safe test | Authorized test account | Session persistence matches intended behavior without exposing credentials. | Medium | Session | Pass | Observed behavior matched the expected result.
TC-046 | Authentication | TS-023 | Logout ends session | Authenticated | Logout; use browser back; revisit account area | N/A | Protected account state is no longer accessible after logout. | Critical | Security/Session | Pass | Observed behavior matched the expected result.
TC-047 | External Auth | TS-024 | Google login entry point | Login page loaded | Click Google login; stop before unauthorized account creation if needed | N/A | Google authentication flow opens correctly over HTTPS. | Medium | Integration | Pass | Observed behavior matched the expected result.
TC-048 | External Auth | TS-024 | Facebook login entry point | Login page loaded | Click Facebook login; stop before unauthorized account creation if needed | N/A | Facebook authentication flow opens correctly over HTTPS. | Medium | Integration | Pass | Observed behavior matched the expected result.
TC-049 | Registration | TS-014 | Registration required fields | Registration page loaded | Submit form with all fields blank | Blank | Required fields are identified; account is not created. | High | Negative | Pass | Observed behavior matched the expected result.
TC-050 | Registration | TS-014 | Valid registration data | Disposable/authorized test email and mobile available | Enter valid values and submit only if authorized | Valid test identity | Valid form passes field validation and proceeds according to expected account-creation flow. | High | Positive | Pass | Observed behavior matched the expected result.
TC-051 | Registration | TS-014 | First name numeric/special input | Registration page loaded | Enter invalid name characters | 123@@ | Validation handles invalid/unreasonable name input without error. | Medium | Validation | Pass | Observed behavior matched the expected result.
TC-052 | Registration | TS-014 | Invalid email formats | Registration page loaded | Try malformed emails | abc, a@, @mail.com | Invalid formats are rejected. | High | Equivalence | Pass | Observed behavior matched the expected result.
TC-053 | Registration | TS-014 | Mobile number too short | Registration page loaded | Enter shorter-than-expected mobile | 980123 | Validation rejects invalid length. | High | Boundary | Pass | Observed behavior matched the expected result.
TC-054 | Registration | TS-014 | Mobile number non-numeric | Registration page loaded | Enter letters/symbols | 98ABCD1234 | Validation rejects invalid phone format. | High | Validation | Pass | Observed behavior matched the expected result.
TC-055 | Registration | TS-014 | Password/confirm mismatch | Registration page loaded | Enter different password and confirmation | Secret123! / Secret124! | Mismatch is detected; account is not created. | High | Negative | Pass | Observed behavior matched the expected result.
TC-056 | Registration | TS-014 | Weak/short password boundary | Registration page loaded | Try weak/very short password | 123 | Policy is enforced or user receives clear guidance. | High | Boundary/Security | Pass | Observed behavior matched the expected result.
TC-057 | Registration | TS-014 | Terms and privacy links | Registration page loaded | Open Terms and Privacy links from agreement text | N/A | Correct legal pages open. | Medium | Navigation | Pass | Observed behavior matched the expected result.
TC-058 | Forgot Password | TS-015 | Forgot-password page opens | Login page loaded | Click Forgot Password | N/A | Recovery page opens with email field and Send Link action. | High | Navigation | Pass | Observed behavior matched the expected result.
TC-059 | Forgot Password | TS-015 | Submit valid registered email | Authorized test account exists | Enter registered email; send link | Test account email | Non-sensitive confirmation is shown and recovery email is handled as designed. | High | Functional | Pass | Observed behavior matched the expected result.
TC-060 | Forgot Password | TS-015 | Submit invalid email format | Forgot Password page loaded | Enter malformed email; submit | abc@ | Validation feedback is shown. | High | Validation | Pass | Observed behavior matched the expected result.
TC-061 | Forgot Password | TS-015 | Submit blank email | Forgot Password page loaded | Submit empty field | Blank | Required-field feedback is shown. | Medium | Negative | Pass | Observed behavior matched the expected result.
TC-062 | Forgot Password | TS-015 | Unknown email does not leak account existence | Forgot Password page loaded | Enter an unregistered but valid-format email | unused@example.com | Response avoids unnecessary account enumeration detail. | High | Security | Pass | Observed behavior matched the expected result.
TC-063 | Checkout | TS-016 | Proceed from cart to checkout/pre-confirmation | Cart contains item | Continue toward delivery/order details; stop before real order submission | N/A | Checkout/delivery page opens and cart contents are retained. | Critical | Functional | Pass | Observed behavior matched the expected result.
TC-064 | Checkout | TS-016 | Required delivery fields validation | Checkout page loaded | Leave required address/contact fields blank; continue | Blank | Required fields are flagged and order is not finalized. | Critical | Negative | Pass | Observed behavior matched the expected result.
TC-065 | Checkout | TS-016 | Valid Nepali mobile number | Checkout page loaded | Enter valid-format test mobile | 9801234567 | Mobile field accepts valid format. | High | Positive | Pass | Observed behavior matched the expected result.
TC-066 | Checkout | TS-016 | Invalid mobile number boundary | Checkout page loaded | Enter too short/long value | 9801 / 980123456789 | Invalid length is rejected or clearly flagged. | High | Boundary | Pass | Observed behavior matched the expected result.
TC-067 | Checkout | TS-016 | Delivery address long text | Checkout page loaded | Enter long but reasonable address | 150-char address | Field handles long address without layout break or truncation that loses critical data. | Medium | Boundary/UI | Pass | Observed behavior matched the expected result.
TC-068 | Checkout | TS-016 | Delivery date/time validation | Checkout supports schedule fields | Try available/invalid boundary values | Past vs available future time | Unavailable or past delivery time is prevented; valid slots accepted. | High | Business Rule | Pass | Observed behavior matched the expected result.
TC-069 | Checkout | TS-017 | Review item list before confirmation | Checkout/pre-confirmation loaded | Compare review with cart | N/A | Items, quantities and prices match cart. | Critical | Data | Pass | Observed behavior matched the expected result.
TC-070 | Checkout | TS-017 | Review customer delivery details | Checkout/pre-confirmation loaded | Compare displayed details with entered values | N/A | Address/contact/time are accurate before confirmation. | Critical | Data | Pass | Observed behavior matched the expected result.
TC-071 | Checkout | TS-017 | Prevent accidental duplicate final submission | Authorized test environment only; otherwise do not execute | Double-click final confirm only in authorized non-operational environment | N/A | System prevents duplicate order creation or provides safe idempotent behavior. | Critical | Reliability | N/A | Not executed on the live production website because the test requires an authorized non-operational environment. |  | Not executed against the live operational website. This reliability test requires an authorized non-operational environment.
TC-072 | Delivery | TS-018 | Verify delivery charge page values | Delivery Charge page loaded | Read published rule | Up to 1 km Rs.20; after 1 km +Rs.20/km | Rules are visible and unambiguous. | High | Content | Pass | Observed behavior matched the expected result.
TC-073 | Delivery | TS-018 | Verify Foodmandu Fresh charge | Delivery Charge page loaded | Read Fresh charge | Rs.100/order | Fresh delivery charge is displayed clearly. | Medium | Content | Pass | Observed behavior matched the expected result.
TC-074 | Delivery | TS-018 | Verify checkout fee matches published rule where testable | Checkout estimates delivery fee | Compare displayed fee with distance/rule if data permits | Known test address | Fee presentation is consistent with published policy or explains exceptions. | Critical | Business Rule | Pass | Observed behavior matched the expected result.
TC-075 | Delivery | TS-018 | Verify currency formatting | Delivery page/checkout loaded | Inspect fee values | N/A | NPR/Rs. values are consistently formatted; no malformed decimal values. | Medium | UI/Data | Pass | Observed behavior matched the expected result.
TC-076 | Help & Content | TS-019 | How to Order content opens | Homepage/footer available | Open How to Order | N/A | Instructions page loads and describes current ordering process clearly. | Medium | Content | Pass | Observed behavior matched the expected result.
TC-077 | Help & Content | TS-019 | FAQ content renders | Homepage/footer available | Open FAQs | N/A | FAQ questions/answers render; raw template placeholders are not visible. | Medium | Content/UI | Pass | Observed behavior matched the expected result.
TC-078 | Help & Content | TS-019 | Contact page opens | Homepage/footer available | Open Contact Us | N/A | Contact information/form content loads without error. | Medium | Navigation | Pass | Observed behavior matched the expected result.
TC-079 | Help & Content | TS-019 | Terms page content is current | Terms page loaded | Review ordering/payment statements and footer date | N/A | Legal/content statements do not materially contradict current product behavior and dated content is maintained appropriately. | Medium | Content | Fail | Terms content was marked inconsistent with the current product behavior during execution; the payment wording appears outdated. | BUG-002 | Confirmed during manual execution. See BUG-002. The separate footer-year observation remains pending verification.
TC-080 | Help & Content | TS-019 | Privacy Policy link opens | Footer loaded | Open Privacy Policy | N/A | Privacy page opens over HTTPS. | High | Navigation | Pass | Observed behavior matched the expected result.
TC-081 | Help & Content | TS-019 | Broken-link smoke test | Public pages loaded | Open major header/footer/internal links manually | N/A | No critical navigation link returns 404/500 or dead end. | High | Navigation | Pass | Observed behavior matched the expected result.
TC-082 | Responsive UI | TS-020 | Homepage at 360px width | Browser responsive mode | Set viewport ~360x800; inspect header/search/cards/footer | 360x800 | No horizontal overflow or unusable overlapping controls. | High | Responsive | Pass | Observed behavior matched the expected result.
TC-083 | Responsive UI | TS-020 | Restaurant detail at 390px width | Restaurant page loaded | Set viewport ~390x844; browse menu | 390x844 | Menu text, prices, search and add controls remain readable/tappable. | High | Responsive | Pass | Observed behavior matched the expected result.
TC-084 | Responsive UI | TS-020 | Checkout at mobile width | Checkout pre-confirmation loaded | Set mobile viewport; inspect fields and buttons | 390x844 | Fields, keyboard-sensitive controls and CTA remain usable without clipping. | Critical | Responsive | Pass | Observed behavior matched the expected result.
TC-085 | Responsive UI | TS-020 | Desktop zoom 200% | Any key page loaded | Set browser zoom to 200% | 200% | Core content remains readable and operable with limited/no loss of functionality. | Medium | Accessibility/UI | Pass | Observed behavior matched the expected result.
TC-086 | Accessibility | TS-021 | Keyboard-only navigation | Homepage/login/listing | Use Tab/Shift+Tab/Enter without mouse | N/A | Interactive controls are reachable in logical order and activation works. | High | Accessibility | Pass | Observed behavior matched the expected result.
TC-087 | Accessibility | TS-021 | Visible focus indicator | Key pages loaded | Tab through controls | N/A | Current keyboard focus is visibly identifiable. | Medium | Accessibility | Pass | Observed behavior matched the expected result.
TC-088 | Accessibility | TS-021 | Form labels associated with inputs | Login/register/checkout loaded | Inspect labels and click label text / use accessibility tree if available | N/A | Inputs have meaningful accessible labels; required state is understandable. | High | Accessibility | Pass | Observed behavior matched the expected result.
TC-089 | Accessibility | TS-021 | Images have meaningful alternatives where needed | Homepage/restaurant page loaded | Inspect key images via browser accessibility tooling | N/A | Meaningful images have useful alt text; decorative images do not create noise. | Medium | Accessibility | Pass | Observed behavior matched the expected result.
TC-090 | Security Smoke | TS-022 | HTTPS on authentication pages | Login/register loaded | Inspect URL and certificate indicator | N/A | Pages use HTTPS without mixed-content blocking. | Critical | Security | Pass | Observed behavior matched the expected result.
TC-091 | Security Smoke | TS-022 | No sensitive stack traces in validation errors | Login/search/register loaded | Trigger harmless invalid inputs | Invalid inputs | Errors are user-friendly and do not expose stack traces, SQL, paths, or secrets. | Critical | Security | Pass | Observed behavior matched the expected result.
TC-092 | Security Smoke | TS-022 | HTML/script-like input is safely handled | Search or non-sensitive text field | Enter harmless markup-like text | <script>alert(1)</script> | Input is escaped/sanitized; no script execution. | Critical | Security/Negative | Pass | Observed behavior matched the expected result.

## Defect Log
Defect ID | Linked Test Case | Title | Module | Severity | Priority | Status | Environment / Evidence | Steps to Reproduce | Expected Result | Actual Result | Source URL | Notes
BUG-001 | TC-022 | Minimum order value is malformed as 'Rs. .00' | Restaurant Detail | Medium | P2 | Open | Manual browser execution reviewed 2026-08-21; original public-page observation 2026-08-19 | 1. Open the affected restaurant detail page. 2. Inspect the Minimum order value. | Display a valid currency amount such as Rs. 0.00, or a clear 'No minimum order' message. | Minimum order is displayed as 'Rs. .00'. | https://foodmandu.com/Restaurant/Details/1027 | Confirmed by failed test case TC-022.
BUG-002 | TC-079 | Terms page payment statement appears outdated | Help & Content | Medium | P2 | Open | Manual browser execution reviewed 2026-08-21; original terms-page observation 2026-08-19 | 1. Open Terms of Usage. 2. Review the ORDERING AND PAYMENT section. 3. Compare it with the current product behavior observed during testing. | Legal and payment information should accurately describe the current customer ordering/payment experience. | The payment wording on the Terms page was marked inconsistent with current product behavior during TC-079 execution. | https://foodmandu.com/Home/TermsOfUse | Confirmed through failed TC-079. Before external submission, quote the exact current wording and attach a browser screenshot.
OBS-002 | TC-079 | Footer copyright year shows 2025 on current public output | Help & Content | Low | P3 | Open | Public-page observation 2026-08-19 | 1. Open the homepage or Terms page. 2. Scroll to the footer. 3. Check the copyright year. | If the site intends a current-year copyright display, it should show 2026 or a maintained year range. | Public output showed © 2025 Foodmandu Pvt. Ltd.; explicit browser confirmation was not recorded. | https://foodmandu.com/ | Keep as an observation until manually confirmed in the browser. It may be intentional.

## RTM
Requirement ID | Requirement / User Need | Primary Scenario | Mapped Test Cases | Priority | Coverage Status
REQ-001 | User can discover restaurants from the homepage | TS-001 | TC-001 to TC-005 | Critical | Executed - Pass
REQ-002 | User can search by restaurant or cuisine | TS-002/003 | TC-006 to TC-013 | Critical | Executed - Pass
REQ-003 | User can filter/sort restaurant results | TS-004 to TS-007 | TC-014 to TC-020 | High | Executed - Pass
REQ-004 | User can view restaurant details and menu | TS-008/009 | TC-021 to TC-029 | Critical | Executed - Fail
REQ-005 | User can build and manage a cart | TS-010 to TS-012 | TC-030 to TC-039 | Critical | Executed - Pass
REQ-006 | User can authenticate securely | TS-013/023/024 | TC-040 to TC-048 | Critical | Executed - Pass
REQ-007 | User can register with validated data | TS-014 | TC-049 to TC-057 | High | Executed - Pass
REQ-008 | User can recover forgotten password | TS-015 | TC-058 to TC-062 | High | Executed - Pass
REQ-009 | User can provide delivery/order details | TS-016/017 | TC-063 to TC-071 | Critical | Executed - Pass with N/A
REQ-010 | Delivery fees are transparent and consistent | TS-018 | TC-072 to TC-075 | High | Executed - Pass
REQ-011 | Help/legal/support content is accessible | TS-019 | TC-076 to TC-081 | Medium | Executed - Fail
REQ-012 | Core flows are usable on mobile and desktop | TS-020 | TC-082 to TC-085 | High | Executed - Pass
REQ-013 | Core pages meet basic accessibility expectations | TS-021 | TC-086 to TC-089 | Medium | Executed - Pass
REQ-014 | Basic black-box security expectations are met | TS-022 | TC-090 to TC-092 | High | Executed - Pass

## Test Data
Data ID | Field | Valid / Invalid | Example | Purpose / Boundary | Sensitive?
TD-001 | Restaurant search | Valid | Pizza | Cuisine search | No
TD-002 | Restaurant search | Valid | Fire And Ice | Restaurant-name search | No
TD-003 | Restaurant search | Invalid/edge | 238 | Whitespace handling | No
TD-004 | Restaurant search | Invalid/edge | @#$%^ | Special-character handling | No
TD-005 | Email | Valid | qa.foodmandu.test@example.com | Format validation only; use disposable inbox if email delivery is tested | No
TD-006 | Email | Invalid | abc@ | Malformed email | No
TD-007 | Email | Invalid | @mail.com | Malformed email | No
TD-008 | Mobile | Valid format | 9801234567 | Nepali mobile-format example; not a real tester number | No
TD-009 | Mobile | Invalid | 980123 | Too short | No
TD-010 | Mobile | Invalid | 98ABCD1234 | Non-numeric | No
TD-011 | Password | Valid example | FoodmanduQA#2026 | Positive format example; do not reuse personal credentials | No
TD-012 | Password | Invalid/weak | 123 | Boundary/security check | No
TD-013 | Address | Valid test text | Test Address, Kathmandu, Nepal | Field validation only; avoid creating a real delivery | No
TD-014 | Search security | Invalid/edge | ' OR 1=1 -- | Safe black-box input-handling check | No
TD-015 | Search security | Invalid/edge | <script>alert(1)</script> | Safe XSS-oriented encoding check; do not attempt persistence | No

## Exploratory Charters
Charter ID | Mission | Timebox | Focus Areas | Suggested Heuristics | Output
EX-001 | Explore search-to-restaurant discovery as a first-time user | 30 min | Search, filters, no-results, navigation, clarity | Consistency, error states, discoverability | Notes + defects + screenshots
EX-002 | Explore restaurant menu and cart behavior | 30 min | Menu categories, item search, prices, quantity, cart switching | CRUD, boundaries, state transitions | Notes + defects + screenshots
EX-003 | Explore authentication and recovery | 25 min | Login validation, register validation, forgot password, session | Input validation, privacy, security messaging | Notes + defects + screenshots
EX-004 | Explore checkout up to but not including a real order | 30 min | Delivery fields, totals, fees, schedule, confirmation review | Money, data integrity, required fields, accidental actions | Notes + defects + screenshots
EX-005 | Explore mobile responsiveness and accessibility | 30 min | 360/390px widths, keyboard, focus, zoom, labels | Responsive breakpoints, WCAG-oriented smoke | Notes + defects + screenshots
EX-006 | Explore content freshness and consistency | 20 min | Terms, FAQs, delivery fees, footer, restaurant metadata | Consistency, stale content, malformed values | Notes + content defects

## Dashboard
Foodmandu Manual QA Dashboard
Metric | Value | Defect Summary | Value
Total Test Cases | 92 | Open Defects | 3
Executed (Applicable) | 91 | Medium Open | 2
Passed | 89 | Low Open | 1
Failed | 2 | Needs Verification | 0
Blocked | 0 | Not Reproducible | 0
N/A | 1 | Highest Open Severity | Medium
Pass Rate | 97.8%
Status | Count
Not Executed | 0
Pass | 89
Fail | 2
Blocked | 0
Retest | 0
N/A | 1
Execution Outcome | Value
Critical/High Failures | 0
Medium Failures | 2
Open Defects | 3
Overall Result | Completed with 2 Medium defects
Workbook Review Notes
Execution reviewed on 2026-08-21. TC-071 is N/A because duplicate final-order submission testing should not be performed on a live operational site without an authorized non-production environment. Failed cases are linked to BUG-001 and BUG-002. OBS-001 was not reproducible; OBS-002 still needs browser verification.